# RC-28 Environmental Permit Conditions

Project: Brookside Avenue Culvert Replacement | Watercourse: Mill Creek Tributary | Permit reference: EP-RC28-2026

# 1. Permit Conditions

| condition_id | condition_area | permit_requirement | trigger_or_limit | status_note |
| --- | --- | --- | --- | --- |
| PC-001 | In-channel work window | In-channel work is allowed only from 2026-08-15 to 2026-09-30. | date window | RC-28 planned work falls inside this window. |
| PC-002 | Rainfall shutdown | Suspend in-channel work when forecast rainfall exceeds 12 mm in the next 24 hours. | 12 mm / 24 hr | Weather check required before excavation and joint sealing. |
| PC-003 | Turbidity limit | Discharge from bypass and work zone shall not exceed 25 NTU above background. | 25 NTU | Daily monitoring required. |
| PC-004 | Fuel setback | Fuel storage and refueling shall be at least 15 m from active channel. | 15 m | Conflicts with pump generator fuel setback of 12 m in RC-28-006. |
| PC-005 | Temporary pedestrian route | Pedestrian route shall maintain at least 1.5 m clear width. | 1.5 m | Conflicts with 1.2 m route listed in traffic staging file. |
| PC-006 | Bypass before excavation | Bypass pumping shall be operational before any culvert removal or flow-path obstruction. | operational before removal | Linked to hold point HP-002. |
| PC-007 | Fish exclusion | Fish exclusion screening shall be installed before bypass startup. | screening installed | No screen mesh size supplied in permit. |
| PC-008 | Sediment control | Sediment controls shall be inspected once daily and after rainfall. | daily and post-rainfall | Linked to HP-007. |
| PC-009 | Condition type missing | Outlet inspection note copied into permit appendix without condition type. | blank condition_type | Missing condition_type field should remain open. |

# 2. Weather and Monitoring Triggers

| weather_id | trigger | threshold | required_action | note |
| --- | --- | --- | --- | --- |
| WT-001 | 24 hour forecast rainfall | > 12 mm | Suspend in-channel work and secure excavation | Weather input required for daily staging. |
| WT-002 | stream flow | greater than 0.45 m3/s | Suspend culvert removal and verify bypass capacity | Compare with RC-28-006 construction check flow 0.42 m3/s. |
| WT-003 | turbidity reading | > 25 NTU above background | Inspect controls and stop discharge until corrected | Daily monitoring log required. |
| WT-004 | forecast data source | blank | Open constraint | No project-specific weather data source named in permit. |

# 3. Permit Appendix Log

| log_id | related_condition | record_type | supplied_value | status_note |
| --- | --- | --- | --- | --- |
| PL-001 | PC-003 | turbidity observation | background 8 NTU, discharge 18 NTU | Text-only monitoring note within limit. |
| PL-002 | PC-005 | pedestrian route observation | 1.2 m clear width shown on staging sketch | Conflicts with 1.5 m permit requirement. |
| PL-003 | PC-004 | fuel setback observation | 12 m generator setback listed in pump staging sketch | Conflicts with 15 m permit requirement. |
| PL-004 | PC-009 | condition owner |  | Missing owner field in permit appendix log. |
| PL-003-DUP | PC-004 | fuel setback observation | 12 m generator setback listed in pump staging sketch | Duplicate of PL-003. |

# 4. Use Limitation

Permit conditions are source requirements for constructability planning. They do not approve temporary works, bypass pumping, traffic control, or excavation methods.